## Projects
Job | Name | Customer | Quoted budget (USD) | Committed cost (USD)
114 | Warehouse fit-out | Northgate Logistics | 60000 | 41200
117 | Hotel retrofit | Harbour Lane Hotels |  | 18400
109 | School extension | Westfield Academy Trust | 85000 | 62300
121 | Office refurbishment | Calder & Finch LLP | 40000 | 22100

## Creditors
ID | Job | Supplier | Description | Amount | Currency | Due (days) | Method | New payee | Accepts split | Defer cost per week (USD) | Unlocks | Notes
PAY-114-FREIGHT | 114 | Rheinfracht Logistik GmbH | Freight for racking system, held at port until paid | 5400 | EUR | 1 | SWIFT | No | No | 350 | REC-114-M2 | Install cannot finish until racking arrives
PAY-117-DEPOSIT | 117 | Klimatech Anlagen GmbH | Deposit on heat-pump equipment | 7500 | EUR | 3 | SWIFT | Yes | No | 0
PAY-109-SUB | 109 | Brightline Electrical Inc | Subcontractor instalment | 2500 | USD | 2 | LOCAL | No | No | 250 |  | Instalment 3 of 6 on agreed payment plan
PAY-121-COMP | 121 | Pennine Joinery Supplies Ltd | Joinery components | 3200 | GBP | 2 | LOCAL | No | Yes | 120 |  | Long-standing supplier; agreed a split twice last year
PAY-OH-SAAS |  | Planwise Software Inc | Annual project-planning software renewal | 850 | USD | 3 | LOCAL | No | No | 0 |  | 14-day grace period on renewals

## Debtors
ID | Job | Customer | Milestone | Amount | Currency | Status | Expected (days) | On-time rate | Early-pay eligible | Customer email
REC-109-M3 | 109 | Westfield Academy Trust | Milestone 3: first-floor shell | 9000 | USD | invoiced | 2 | 0.92 | No | accounts@westfield-academy.example
REC-121-INV | 121 | Calder & Finch LLP | Stage 2: ground-floor fit-out | 12000 | USD | invoiced | 21 | 0.95 | Yes | payables@calderfinch.example
REC-114-M2 | 114 | Northgate Logistics | Milestone 2: racking installed | 24000 | USD | blocked | 30 | 0.88 | No | ap@northgate.example